## Monthly Timesheet
September 2026 Timesheet
Sr No. | Date | Day | Project Name | Dev Name | Task Details | Working Hours | Status | Total Hours
1 | 01/09/2026 | Tuesday | MargNetra Super App | Soudip | Architecture planning and technical requirement mapping for global API services and exception handling | 4.5 | Completed
[5 empty] | Setting up network client abstraction, error response classes, and failure recovery data models | 4.5
2 | 02/09/2026 | Wednesday | MargNetra Super App | Soudip | Implemented AppExceptionHandler for centralized error handling, HTTP error parsing, and user error alerts | 4.5 | Completed
[5 empty] | Configured base API services, URL constants, and data provider interfaces (api_constants.dart, api_urls.dart, data_provider.dart) | 4.5
3 | 03/09/2026 | Thursday | MargNetra Super App | Soudip | Integrated AppExceptionHandler into global app error boundary in main.dart (Git Commit 0bb42f6) | 4.5 | Completed
[5 empty] | Redesigned ProfilePage layout with updated user details, avatar styling, and responsive profile container | 4.5
4 | 04/09/2026 | Friday | MargNetra Super App | Soudip | Added user profile form validation, edit profile dialogs, and dynamic user account data binding | 4.5 | Completed
[5 empty] | Implemented routing updates and navigation state persistence across authentication flows | 4.5
5 | 07/09/2026 | Monday | MargNetra Super App | Soudip | Family Circle module enhancement: refined map view and list view toggle transitions and member cards | 4.5 | Completed
[5 empty] | Implemented member safe zone radius indicator and emergency circle alert trigger logic | 4.5
6 | 08/09/2026 | Tuesday | MargNetra Super App | Soudip | Bounty Capture feature: glowing circular countdown widget and video recorder state handler | 4.5 | Completed
[5 empty] | Added checklist validation for video recording quality and preview dialog before upload | 4.5
7 | 09/09/2026 | Wednesday | MargNetra Super App | Soudip | Traffic E-Challan page: status filter tabs (Pending/Paid), fine breakdown cards, and search filtering | 4.5 | Completed
[5 empty] | Legal Vault page: categorized document cards (RC, DL, Insurance, Pollution) and secure viewer interface | 4.5
8 | 10/09/2026 | Thursday | MargNetra Super App | Soudip | MgcWalletWidget: wallet current balance card, quick action buttons, and transaction history list layout | 4.5 | Completed
[5 empty] | Wallet recharge bottom sheet: amount quick-select chips, payment method hooks, and validation | 4.5
9 | 11/09/2026 | Friday | MargNetra Super App | Soudip | NavigationHomePage: enhanced bottom bar styling, active tab indicators, and notification badge counts | 4.5 | Completed
[5 empty] | Dark/Light theme consistency check, color palette alignment, and widget test cases | 4.5
10 | 14/09/2026 | Monday | Medlif | Soudip | Designed PDF generator service for clinical prescriptions using ReportLab (pdf_generator.py) | 4.5 | Completed
[5 empty] | Implemented dynamic lab report PDF template with medical parameters and doctor signature block | 4.5
11 | 15/09/2026 | Tuesday | Medlif | Soudip | Database verification scripts for appointment scheduling, doctor availability, and department slots | 4.5 | Completed
[5 empty] | Seeded mock clinical prescriptions, patient history, and diagnostic lab test reports | 4.5
12 | 16/09/2026 | Wednesday | Medlif | Soudip | Configured Postman collection for MedLif Payments & Razorpay checkout integration | 4.5 | Completed
[5 empty] | Tested payment webhook handler, automated invoice generation, and refund status logging | 4.5
13 | 17/09/2026 | Thursday | Medlif | Soudip | MedLif Billing Dashboard audit: revenue metrics, department-wise earnings, and invoice queries | 4.5 | Completed
[5 empty] | Executed automated billing tests and validated PDF download endpoint response headers | 4.5
14 | 18/09/2026 | Friday | Medlif | Soudip | Executed full QA automated audit script (full_qa_audit.py) across clinical & ops endpoints | 4.5 | Completed
[5 empty] | Compiled MedLif Clinical Audit Report (MedLif_Clinical_Audit_Report.md) and resolved portal bugs | 4.5
15 | 21/09/2026 | Monday | MargNetra Super App | Soudip | Initialized MargNetra FastAPI backend repository (margentra_super_app_backend_python) | 4.5 | Completed
[5 empty] | Configured ASGI application lifecycle, CORS middleware, Pydantic schemas, and SQLAlchemy async DB engine | 4.5
16 | 22/09/2026 | Tuesday | MargNetra Super App | Soudip | Implemented JWT authentication, password hashing, and user registration endpoints (auth.py) | 4.5 | Completed
[5 empty] | Built user profile management, emergency contact APIs, and OAuth security dependencies | 4.5
17 | 23/09/2026 | Wednesday | MargNetra Super App | Soudip | Prepared comprehensive MargNetra_API_Requirements.xlsx covering 50 endpoints across 12 modules | 4.5 | Completed
[5 empty] | Implemented Trip management service & API endpoints (trips.py, trip_service.py) with live tracking logic | 4.5
18 | 24/09/2026 | Thursday | MargNetra Super App | Soudip | Implemented Wallet, Challans, Legal Vault, DigiLocker, and SOS emergency dispatch endpoints | 4.5 | Completed
[5 empty] | Configured WebSockets live telemetry router and Pytest test suite (test_auth.py, test_trips.py, test_wallet.py) | 4.5
19 | 25/09/2026 | Friday | MargNetra Super App | Soudip | Implemented BluetoothService for BLE peripheral scanning, RSSI filtering, state machine, and GATT communication | 4.5 | Completed
[5 empty] | Built BluetoothScanPage with radar pulse animation, BTDeviceTile, BTConnectBanner, and pushed commit fa38d26 | 4.5
20 | 28/09/2026 | Monday | MargNetra Super App | Soudip | Integrated Flutter Bluetooth Cab service with FastAPI WebSockets telemetry broadcast | 4.5 | Completed
[5 empty] | LiveDriveStatusSosWidget integration with backend alert dispatcher and trip event handler | 4.5
21 | 29/09/2026 | Tuesday | MargNetra Super App | Soudip | End-to-end integration testing: Digital Wallet balance sync, top-up API, and e-Challan lookup | 4.5 | Completed
[5 empty] | Bug fixes in BLE reconnection handler, timeout safeguards, and error boundary alerts | 4.5
22 | 30/09/2026 | Wednesday | MargNetra Super App | Soudip | Android release build optimization, APK testing on physical test device, and memory profiling | 4.5 | Completed
[5 empty] | Sprint review, API documentation update, and September month deliverables sign-off | 4.5
MONTHLY TOTAL WORKING HOURS

## Executive Summary
MARGNETRA SUPER APP — SEPTEMBER 2026 WORK REPORT
Developer Name: | Soudip Samanta |  | Role / Designation: | Software Developer (Flutter & Python Backend)
Company / Org: | Netfotech Solutions |  | Reporting Month: | September 2026 (01/09/2026 – 30/09/2026)
Primary Workspaces: | d:\office_dev\margnetra_super_app & margentra_super_app_backend_python |  | Total Working Days: | 22 Days (198 Working Hours)
KEY METRICS & SPRINT ALLOCATION
Project / Workstream | Platform / Tech Stack | Days Allocated | Total Hours | % Allocation | Key Milestone Delivered
MargNetra Super App (Frontend) | Flutter, Dart, Provider/Bloc, BLE | 12 | 108 | 54.5% | Bluetooth BLE Cab Integration, Scan Radar UI, Exception Architecture (Commits fa38d26, 0bb42f6)
MargNetra Super App (Backend) | Python, FastAPI, SQLAlchemy, WebSockets, Docker | 5 | 45 | 22.7% | FastAPI Backend Architecture, 50 API Endpoints, JWT Auth, WebSockets Telemetry, Postman Collection
MedLif Healthcare Backend | Python, ReportLab, QA Audit, Billing/Payments | 5 | 45 | 22.7% | Clinical Prescriptions PDF Generator, MedLif QA Clinical Audit Report, Payment Webhooks
TOTAL SEPTEMBER WORK | Full-Stack Mobile & Backend | 22 | 198 | 100.0% | All Deliverables Successfully Implemented, Tested, Documented & Pushed

## Technical Features Breakdown
SEPTEMBER 2026 — TECHNICAL DELIVERABLES BREAKDOWN
Module / Feature | Tech Stack | Component / File References | Key Implementation Highlights | Business / Functional Impact
Bluetooth Cab Integration & Radar Scanning | Flutter (Dart), flutter_blue_plus, Android BLE | lib/core/app_services/bluetooth_service/bluetooth_service.dart lib/pages/all_nav_pages/bluetooth_connect_cab_page/bluetooth_scan_page.dart widgets/bt_communication_panel.dart, bt_connect_banner.dart, bt_device_tile.dart | Built complete BLE service for device discovery, dynamic RSSI calculation, GATT UUID communication, pulse radar scanning UI, device pairing confirmation modals, and Android Manifest Bluetooth permissions. | Allows users to seamlessly pair their smartphone with vehicle cabs for automated trip telemetry, status tracking, and emergency response.
Global App Exception Architecture | Flutter, Dart | lib/core/app_exception_handler/app_exception_handler.dart lib/main.dart lib/core/app_services/api_services/api_constants.dart, api_urls.dart, data_provider.dart | Centralized error handling engine catching runtime and HTTP exceptions, formatting user-friendly dialogs, preventing app crashes, and establishing structured API configuration. | Dramatically improves application reliability and provides clean error boundaries for all upcoming backend integrations.
Profile & Navigation UI Overhaul | Flutter, Custom Painters | lib/pages/profile_page/profile_page.dart lib/pages/navigation_home_page/navigation_home_page.dart lib/pages/family_circle_page/family_circle_page.dart | Redesigned user profile interface, avatar handling, form validations, bottom navigation bar active state styling, and Family Circle live tracking toggle. | Elevates application aesthetics to premium corporate standard with intuitive ergonomics.
MargNetra Backend Architecture & Core Services | Python 3.12, FastAPI, SQLAlchemy Async, Pydantic v2 | app/main.py, app/core/security.py, app/db/session.py app/api/v1/endpoints/auth.py, users.py, trips.py, wallet.py, challans.py, legal.py, digilocker.py, family.py, sos.py, bounty.py, devices.py | Built modular ASGI backend containing 50 API endpoints across 12 modules, JWT bearer auth with bcrypt password hashing, asynchronous database queries, and structured schemas. | Provides end-to-end backend services powering the entire MargNetra mobile ecosystem.
Real-Time Telemetry & WebSockets Engine | FastAPI WebSockets, Python Asyncio | app/api/v1/endpoints/websockets.py app/ws/events.py app/services/trip_service.py | Duplex WebSocket connection for streaming cab telemetry, live GPS coordinates, status transitions, and immediate SOS distress broadcast to emergency contacts. | Enables sub-second latency for cab tracking and critical safety features.
MedLif Healthcare Clinical PDF & QA Audit | Python, ReportLab, Pytest, Postman | pdf_generator.py, MedLif_Clinical_Audit_Report.md Medleaf_Billing_Dashboard_Postman.json, Medleaf_Payments_Postman_Collection.json scratch/full_qa_audit.py | Implemented automated PDF generation for patient prescriptions and lab reports; executed complete QA audit of billing, payments, and clinic endpoints. | Ensures MedLif production stability, accurate medical report formatting, and reliable billing compliance.

## Git Commits & Deliverables
MARGNETRA SUPER APP — GIT COMMIT LOG & CODE REPOSITORY STATS
Commit Hash | Commit Date | Author | Commit Message | Files Changed | Lines Added / Deleted
fa38d26 | 25/09/2026 17:07 | Netfotech Soudip <soudip@netfotech.in> | feat: add Bluetooth connectivity service and scan UI for cab integration | 15 files changed (bluetooth_service.dart, bluetooth_scan_page.dart, bt_device_tile.dart, bt_communication_panel.dart, bt_connect_banner.dart, AndroidManifest.xml, etc.) | +1,784 additions -116 deletions
0bb42f6 | 03/09/2026 17:49 | Netfotech Soudip <soudip@netfotech.in> | feat: Add exception handling classes and update profile page layout | 6 files changed (app_exception_handler.dart, api_constants.dart, api_urls.dart, data_provider.dart, profile_page.dart, main.dart) | +60 additions -4 deletions
Backend Codebase | 21/09/2026 – 25/09/2026 | Netfotech Soudip | FastAPI MargNetra backend microservices, JWT security, 50 API endpoints, SQLAlchemy models, WebSockets, Alembic migrations, Pytest suite, and Docker containerization | 52 files created across app/, alembic/, tests/, and root | +4,200+ additions
Documentation & API Spec | 23/09/2026 | Netfotech Soudip | MargNetra_API_Requirements.xlsx & MargNetra_Super_App.postman_collection.json | Comprehensive API requirements matrix (50 APIs, 12 modules) and Postman test environment | 7 sheets, complete spec